## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE
EXPECTED COMPLETION DATE
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To develop a full-stack web application called College Finder that helps students search and discover colleges in India based on course name and city. The system should provide college details such as college name, location, available courses, and contact information through a simple and user-friendly interface.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Students often struggle to find suitable colleges because information is scattered across multiple websites. Manual searching is time-consuming and inefficient. This project provides a centralized platform where students can search colleges quickly using filters like course and city. It improves accessibility, saves time, and supports better educational decision-making. The preferred solution is a searchable web platform using Node.js, Express.js, MySQL, HTML, CSS, and JavaScript because it is cost-effective, scalable, and easy to maintain.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Complete project within 5 days (19-04-2026 to 24-04-2026) Build working frontend and backend successfully Connect MySQL database without errors Implement accurate search by course and city Achieve successful testing of all core functionalities Prepare project for deployment using free hosting platforms
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | Responsive frontend UI using HTML, CSS, JavaScript Backend server using Node.js and Express.js MySQL database with college and course records Search functionality using filters Dynamic result display Testing documents and test reports SRS document RAID log Lessons learnt log Project report Deployment-ready project structure
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | College search by course name College filtering using city Display college details dynamically Responsive frontend UI Backend API development MySQL database connection Data insertion and retrieval Testing and debugging Basic deployment preparation
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Full admin panel JWT authentication system User login and registration system College comparison feature Admission application system Payment integration Advanced analytics dashboard
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 Developer (T. Mohan Ranga) 1 Mentor 1 Project Reviewer Total active development resource: 1
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Laptop/Desktop Internet connection Visual Studio Code Node.js Express.js MySQL Server Browser for testing GitHub (optional)
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Resource--Cost Allocation Developer--Internship Project Laptop--Existing Personal Resource Internet --Existing Personal Resource VS Code--Free Node.js--Free Express.js--Free MySQL--Free
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Talisetty Mohan Ranga
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Students (Primary Users) Project Mentor Project Reviewer Cloud Counselage Pvt. Ltd. Developer/Admin
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | MySQL database connection failure Backend API errors Deployment issues using free hosting Short project timeline Frontend integration issues
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | Users mainly need simple college search functionality Core features are more important than advanced features Separate frontend/backend deployment is acceptable Free hosting platforms will be sufficient for submission
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | Only 5 days available for project completion Limited free hosting options Beginner-level development experience Time limitation for advanced features No paid cloud database services
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 04-19-2026
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 04-20-2026
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 04-21-2026
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 04-22-2026
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 04-23-2026
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 04-24-2026
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 04-26-2026