## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | College Finder |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Vinith Christopher
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS | Column1
1 | 2026-04-20 | MySQL connection failed during backend setup | Technical | Database access denied error in terminal | Verify credentials before starting backend development | Corrected MySQL username and password configuration | Developer | Closed | Helped avoid repeated backend failures
2 | 2026-04-21 | Search API was not returning proper results | Debugging | Empty results despite valid search input | Test SQL queries separately before API integration | Fixed SQL query logic and improved filtering | Developer | Closed | Improved backend reliability
3 | 2026-04-22 | Frontend showed blank page during API integration | Frontend Development | UI loaded without displaying results | Use browser console and inspect errors immediately | Debugged JavaScript rendering and API response handling | Developer | Closed | Improved frontend stability
4 | 2026-04-23 | Deployment planning created issues with free hosting | Deployment | Backend and database were difficult to host together | Research deployment options earlier in project timeline | Planned separate deployment strategy using free platforms | Developer | Closed | Static frontend backup was prepared
5 | 2026-04-24 | Time shortage for advanced features like admin panel | Project Management | Core features taking more development time | Prioritize must-have features before optional features | Focused on search functionality and final testing first | Developer | Closed | Helped complete project within 5 days
d